# LOCAL SEO NEXT STEPS – ELITE EXTERIORS (Chesapeake, VA)

Goal: Move into the local 3‑pack for “pressure washing chesapeake” and rank page 1 for core terms while increasing conversions.

1) FOUNDATION AND DOMAIN

[ ] Keep elitexteriorsva.com as the primary site (Netlify).

[ ] In Wix (elitxteriors.com), set 301 domain forwarding to https://elitexteriorsva.com (www and root).

[ ] Verify HTTPS on elitexteriorsva.com, correct canonical URLs, and HSTS.

[ ] Update all references to the new email: info@elitexteriorsva.com.

[ ] Submit updated sitemap.xml in Google Search Console and Bing Webmaster Tools.

[ ] Ensure robots.txt allows crawling and includes sitemap.

2) GOOGLE BUSINESS PROFILE (GBP)

[ ] Primary Category: Pressure washing service.

[ ] Secondary Categories: Gutter cleaning service; Window cleaning service; Exterior cleaning service; Power washing contractor; Roof cleaning service; Deck cleaning service; Siding cleaning service.

[ ] Service Areas: Chesapeake, Virginia Beach, Norfolk, Portsmouth, Suffolk, Hampton Roads.

[ ] Add 20+ geo‑tagged photos (before/after) over 4 weeks.

[ ] Add Products/Services in GBP (each key service with description, price range, and CTA).

[ ] Post 3–4 times/week (What’s New, Offer, Before/After, Seasonal tip).

[ ] Seed the Q&A section (5–10 common questions with authoritative answers).

[ ] Goal: 50+ reviews at 4.9–5.0 stars within 90 days (see Review flow).

3) WEBSITE PAGES TO BUILD/OPTIMIZE (NEXT.JS)

Priority pages

[ ] Locations hub: /locations (links to all city pages).

[ ] Chesapeake location page: /locations/chesapeake (hero, trust stats, services, neighborhoods, FAQs, schema).

[ ] Additional city pages (stagger weekly): Virginia Beach, Norfolk, Portsmouth, Suffolk.

[ ] Core service pages: House Washing, Roof Cleaning, Driveway/Concrete, Gutter Cleaning, Window Cleaning, Commercial Power Washing.

[ ] Add FAQ sections on all service/location pages and implement FAQPage schema.

Technical implementation

[ ] Add LocalBusiness schema to each location page (name, phone, address/area served, hours, sameAs).

[ ] Add Service schema to each core service page.

[ ] Add BreadcrumbList schema sitewide.

[ ] Internal linking: service <> location <> blog <> gallery; use descriptive anchors with target keywords.

[ ] Accessibility: no gray text on white; use high‑contrast text; ensure readable link colors; heading hierarchy correct.

[ ] Core Web Vitals: LCP < 2.5s, CLS < 0.1, INP < 200ms. Optimize images (WebP), lazy‑load, preload hero font, reduce JS, cache headers set in netlify.toml.

[ ] Create “Results” gallery with filterable before/after by city/service.

[ ] Prominent CTAs: sticky mobile call bar + “Get a Free Quote” on all pages.

[ ] Add conversion events (phone click, form submit) to GA4.

[ ] Ensure forms post to Netlify Forms with spam honeypot.

4) CONTENT PLAN (90 DAYS)

Blog (publish weekly)

[ ] Ultimate Guide to Pressure Washing in Chesapeake, VA.

[ ] 5 Signs Your Chesapeake Home Needs Pressure Washing Now.

[ ] Soft Wash vs. Pressure Wash: What Chesapeake Homeowners Should Know.

[ ] Neighborhood Spotlight: Greenbrier Exterior Cleaning Tips.

[ ] Seasonal: Fall Gutter Cleaning Checklist for Chesapeake.

Assets

[ ] 8 case studies (before/after) with detailed process, chemicals, time, results, neighborhood.

[ ] 3 explainer videos (soft wash vs pressure; driveway cleaning; roof algae treatment).

[ ] Social posts: 3–4/week (use before/after reels, reviews, tips).

5) REVIEWS ENGINE (VELOCITY + QUALITY)

[ ] Implement post‑job SMS + email auto‑sequence within 24 hours (link to GBP).

[ ] Follow‑up if no review in 3 days; final nudge at 10 days.

[ ] QR code on invoices/door hangers.

[ ] Reply to every review within 24 hours using keyword‑rich, location‑aware responses.

Targets: +5–10 new reviews/month until 50+.

6) CITATIONS (NAP CONSISTENCY)

Tier 1 (ASAP)

[ ] Google Business Profile, Bing Places, Apple Maps, Yelp, Facebook, BBB, Angi, HomeAdvisor, Thumbtack, Nextdoor.

Local/Industry (weeks 2–6)

[ ] Chesapeake Chamber, Hampton Roads directories, 757 services directories, PWNA, Pressure Washing Resource Association, local neighborhood/business lists.

[ ] Ensure exact NAP: Elite Exteriors | Chesapeake, VA | (your phone) | https://elitexteriorsva.com | info@elitexteriorsva.com

7) BACKLINKS (LOCAL AUTHORITY)

[ ] Sponsor 2–3 Chesapeake youth teams or community events (earn .org backlinks).

[ ] Pitch seasonal home‑care tips to local news; submit press releases (earned media links).

[ ] Partner with 5 local realtors/HOAs/property managers for resources pages links.

[ ] Join Chamber and get member directory link.

[ ] Publish 8 case studies and interlink from GBP posts and social.

Goal: 5–10 quality local backlinks/quarter; 50 over 12 months.

8) KEYWORDS TO OWN (PRIMARY SET)

[ ] pressure washing chesapeake

[ ] power washing chesapeake va

[ ] house washing chesapeake

[ ] roof cleaning chesapeake

[ ] driveway cleaning chesapeake

[ ] gutter cleaning chesapeake

[ ] window cleaning chesapeake

9) TRACKING AND GOALS

[ ] GA4 + GSC installed and verified; create events: phone_click, quote_request, service_view_30s.

[ ] Call tracking (CallRail): unique number on location pages; record calls.

KPIs (90 days)

- Local 3‑pack: Top 3 for “pressure washing chesapeake”.

- Organic rankings: Page 1 for primary keywords.

- Reviews: 50+ total; 5–10/month.

- Conversions: 5% call rate; 3% form rate; 60% close rate from quotes.

- Backlinks: +10 local links; +40 citations.

10) WEEK‑BY‑WEEK EXECUTION (FIRST 8 WEEKS)

Week 1

[ ] Wix 301 to elitexteriorsva.com; sitemap to GSC; GBP categories/areas updated; add 10 photos; publish Chesapeake location page; enable GA4 events and call tracking.

Week 2

[ ] Service pages (House, Roof, Driveway) + schema; 5 citations; 2 GBP posts; start review workflow; 1 blog post.

Week 3

[ ] Virginia Beach location page; 5 citations; 2 GBP posts; 1 case study; outreach to 3 partners; add sticky mobile call bar.

Week 4

[ ] Norfolk location page; 5 citations; 2 GBP posts; 1 blog; compress images + lazyload audit; add FAQs.

Week 5

[ ] Portsmouth location page; 5 citations; 2 GBP posts; secure 1 sponsorship; 1 case study.

Week 6

[ ] Suffolk location page; 5 citations; 2 GBP posts; 1 blog; push to local news with seasonal tip.

Week 7

[ ] Gallery/case study hub; internal link audit; add Review schema to testimonials; post 10 new photos to GBP/social.

Week 8

[ ] Core Web Vitals tune‑up; build 5 more citations; partner follow‑ups; 1 blog + 1 video; review KPI progress and iterate.

11) DEV TASKS FOR THIS REPO

[ ] Create /locations index and Chesapeake page (already scaffolded if present).

[ ] Add schema components (LocalBusiness, Service, FAQ).

[ ] Add sticky mobile conversion bar component.

[ ] Ensure high‑contrast text classes across legal and content pages (no gray on white).

[ ] Netlify forms and spam honeypot confirmed; success tracking events fired.

[ ] Update footer with links to Privacy, Terms, Cookie Policy, and Locations.

[ ] Add sitemap route regeneration on build; verify robots.

12) CONTENT SOURCES NEEDED

[ ] Final service list, pricing ranges, neighborhoods list, insurance/license details.

[ ] 20+ before/after photos; 3 short vertical videos.

[ ] Customer testimonials to seed reviews and case studies.

DONE MEANS: The item is executed in production, measured in GA4/GSC, and reflected in GBP visibility.